UMURAVA · SOCIAL MEDIA MANAGEMENT Challenge 4: The Live Architect LinkedIn Live Launch Event — AI-Powered Resume Optimization Events & Engagement Strategy · 3-Day Buzz Plan · Content Multiplier · Success Metrics

OVERVIEW Umurava is launching AI-Powered Resume Optimization. As the event architect, you are responsible for the full lifecycle — from the first teaser post to final performance reporting. This document covers all three tasks: the 3-Day Buzz Plan, Post-Event Content Multiplier, and Measurement of Success.

Task 1 — The 3-Day Buzz Plan

The goal is simple: build genuine momentum across three days leading up to the LinkedIn Live launch. Each day has a distinct emotional purpose — curiosity, conviction, and urgency — and together they move a cold audience from awareness to active attendance.

DAY 1 — THE TEASE

| Day 1 9:00 AM | BRAND AWARENESS · Static Graphic "Something is changing for African talent. Forever." A mystery post that names the universal pain point — sent out 20 applications and heard nothing back — without revealing the feature. Drives curiosity, early follows, and LinkedIn algorithmic activation before a single dollar is spent on promotion. #Umurava · #AIForAfrica · #CareerTech · #ComingSoon · #AfricanTalent Why this works: Emotional specificity makes the hook personal and shareable. Early comments signal to LinkedIn's algorithm that the page is active — boosting organic reach for Days 2 and 3 before the event has even been named. |
| --- | --- |

DAY 2 — THE VALUE

| Day 2 10:00 AM | EDUCATION & ANTICIPATION · Carousel · 5 Slides "Why do qualified candidates get ignored? The uncomfortable truth." Educates the audience on ATS filtering — the invisible barrier killing most applications — then positions Umurava's new feature as the direct solution. Lists exactly what attendees will learn at the live session. Registration link goes live alongside this post. #ResumeOptimization · #AITools · #JobSearchAfrica · #Umurava · #CareerGrowth Why this works: Shifting from mystery to concrete value converts curious followers into committed attendees. The Share with a friend CTA turns existing followers into a free distribution channel — extending reach well beyond Umurava's owned audience at zero extra cost. |
| --- | --- |

DAY 3 — THE REMINDER

| Day 3 8:00 AM | URGENCY & FOMO · Short Video · 60 Seconds "We go LIVE in less than 24 hours. Here's what you'll miss if you skip this." Three deliberate FOMO triggers layered in sequence: a live AI demo (an exclusive real-time experience), a live Q&A session (direct access impossible from a replay), and a 48-hour replay limit (scarcity). Time zones listed explicitly — EAT, WAT, GMT — to eliminate friction for the African diaspora. #LinkedInLive · #Umurava · #AIResume · #GetHired · #AfricanTalent · #CareerTech Why this works: Scarcity plus exclusivity plus accessibility. Listing time zones removes the top reason remote-first African audiences miss events. The tag-a-friend CTA brings in warm referrals in the final hours — historically the highest-converting audience segment for live events. |
| --- | --- |

EVENT TIMELINE Day -3 at 9:00 AM: Mystery teaser drops. Comments pour in. Algorithms activates. ¦ Day -2 at 10:00 AM: Carousel reveals the value. Registration link goes live. ¦ Day -1 at 8:00 AM: Final FOMO video. Bell notification CTA. Tag-a-friend push. ¦ Event Day: LinkedIn Live — 30-minute AI-Powered Resume Optimization launch. Real demo. Real Q&A.

Task 2 — The Post-Event Content Multiplier

The live event ends — but the content strategy does not. A 30-minute LinkedIn Live recording is not a finished product. It is a content library. The goal is to extract maximum reach and impact from a single session by repurposing it into three platform-native pieces, each engineered for a specific audience and format.

CONTENT PIECE 1

| X (Twitter) 8-Tweet Thread | TIMING: Within 4 hours of the event ending "We just went live with 1,200+ talents. Here are 7 reasons qualified African candidates are filtered out before a recruiter ever reads their name." Pull the most shareable, standalone insights from the session and structure them as a numbered thread. Each tweet must deliver value independently — someone who only reads tweet 3 still gets something useful. The final tweet links to the full replay with a 48-hour scarcity reminder attached. Why it works: A thread with one punchy insight per tweet earns saves, retweets, and quote tweets — each one a separate distribution event reaching audiences Umurava does not yet own. Long-tail discoverability through hashtags extends the thread's reach for days after posting. |
| --- | --- |

CONTENT PIECE 2

| Instagram / TikTok 60-Sec Vertical Reel | TIMING: 24–48 hours after the event "We ran a real resume through our AI live on screen. What happened next shocked even us." Pull the single most surprising moment from the session — the live demo result or the most impactful Q&A answer. Edit into a punchy, captioned vertical clip with on-screen text and Umurava branding. End every version with: Full replay in bio — 48 hours only. Why it works: Short-form video rewards emotional hooks and fast payoff. A 60-second clip that delivers a genuine wow moment earns saves and shares — driving cold audiences who missed the live event to seek out the full replay entirely on their own. |
| --- | --- |

CONTENT PIECE 3

| LinkedIn 6-Slide Carousel Recap | TIMING: 48 hours after the event "You missed Umurava's LinkedIn Live. Here's everything that was covered — in 6 slides." One major insight or demo highlight per slide, in clean Umurava-branded design. The final slide thanks attendees and invites those who missed the live session to join the Umurava platform or register for the next event in the series. Why it works: Carousels consistently outperform standard posts because each swipe is a dwell-time signal in LinkedIn's algorithm. Posting 48 hours later captures a completely different audience segment — those who were not online during the live — effectively doubling the event's total organic reach. |
| --- | --- |

Task 3 — Measurement of Success

Vanity metrics do not tell the full story. The four metrics below are chosen specifically because each one connects social media activity to a real, trackable business outcome for Umurava — not just a number that looks good in a report.

METRIC 01

| 01 | Live Attendance Rate Percentage of registered people who actually attended the live event Registration numbers feel impressive but mean very little without context. A high attendance rate proves the 3-day buzz plan built genuine intent — not just passive sign-ups. The industry benchmark for LinkedIn Live is 30–40% of registrations showing up. Beating that benchmark validates the entire pre-event content strategy and confirms the audience trusts Umurava enough to show up in real time. Target: 30–40% attendance rate (LinkedIn Live industry benchmark) |
| --- | --- |

METRIC 02

| 02 | Live Engagement Rate Comments, questions and reactions recorded during the 30-minute broadcast Engagement during the live session is the clearest real-time signal of content resonance — it separates passive viewers from actively invested ones. High comment volume specifically during the AI demo indicates genuine product curiosity, which is a warm lead indicator. Questions asked live also provide direct market research: what people ask reveals exactly what content gaps Umurava needs to address in future sessions. |
| --- | --- |

METRIC 03

| 03 | Post-Event Platform Sign-Ups New talent registrations or profile completions on Umurava within 72 hours of the event This is the bottom-of-funnel metric that bridges social media activity to real business impact. A measurable spike in sign-ups or completed profiles in the 72-hour window after the event proves the session was converting — not just entertaining. It directly ties the social media team's work to Umurava's core growth objective: expanding and activating its talent pool on the platform. Target: Measure the 0–72 hour window post-event; compare to baseline week-on-week |
| --- | --- |

METRIC 04

| 04 | Repurposed Content Reach Combined views, saves and shares across X, Instagram/TikTok and LinkedIn carousel in the 7 days following the event The live event reaches one audience at one specific moment. The repurposed content is what multiplies the return on investment of the entire production. Tracking combined reach across platforms reveals which formats and channels resonate with which audience segments — intelligence that directly improves every future campaign. High replay views also extend the feature launch's visibility for weeks after the live session has ended. Target: Track each platform separately over a 7-day post-event window; identify top-performing format |
| --- | --- |

The event is a moment. The strategy is what makes it last. Umurava · AI-Powered Resume Optimization · LinkedIn Live Launch

FULLY PRESENTATION IN UMURAVA THEME COLOR